TECHNICAL PROJECT PROPOSAL

Internal Company Hub

Self-Hosted Knowledge Base, Project Management & Information Platform

| Document Type | Technical Project Proposal |
| --- | --- |
| Version | 1.0 |
| Date | 20 March 2026 |
| Author | Andreas Pieri |

TABLE OF CONTENTS

1. Executive Summary	3

2. Hardware & Connectivity	4

2.1 Server Specification	4

2.2 Remote Access Model	4

2.3 Latency & Performance	4

3. Software Stack	5

3.1 Knowledge Base & Information Platform (Unified)	5

3.2 Custom Project Manager	5

4. Migration Plan	6

5. Post-Launch Testing Environment	7

5.1 Why a Testing Environment Is Required	7

5.2 Architecture	7

5.3 Cost Impact	7

6. Security Architecture	8

7. Next Steps	9

# 1. Executive Summary

This presents the design and implementation plan for an Internal Company Hub: a unified, self-hosted digital workspace that consolidates documentation, project management, and internal communications into a single branded platform. The Hub replaces SharePoint and give Jira like environment with purpose-built open-source alternatives hosted on a dedicated Virtual Private Server (VPS) in a professional off-site data centre.

The Hub will deliver two services:

- Knowledge Base & Information Platform – A single BookStack instance serving as both the company wiki (policies, procedures, documentation) and the information release channel (software release notes, policy updates, company announcements). This replaces SharePoint entirely.

- Custom Project Manager – A tailored alternative to Jira (OpenProject or Taiga), stripped of unnecessary complexity and configured to match the team’s actual workflows.

By self-hosting on open-source software, the organisation gains full ownership of its data, eliminates recurring per-seat licensing fees, and ensures that every interface element — from logos to navigation menus — can be customised to reflect corporate branding. All services are accessed through clean web URLs; no command-line knowledge is required for end users.

# 2. Hardware & Connectivity

## 2.1 Server Specification

The Hub runs on a VPS provisioned with four dedicated CPU cores and flexible, scalable RAM. This configuration handles multiple containerised services (web server, database, reverse proxy) running in parallel, while scalable RAM allows the allocation to grow on demand without a hardware migration.

| Component | Specification | Rationale |
| --- | --- | --- |
| CPU | 4 Dedicated Cores | Handles concurrent web requests, database queries, and background tasks without contention. |
| RAM | Scalable / Flexible | Start with a lean allocation, scale upward as services and users grow. No over-provisioning. |
| Storage | SSD (NVMe preferred) | Near-zero latency for database reads/writes. Critical for fast wiki searches and page loads. |
| Network | Data-centre uplink | High-bandwidth, low-latency connectivity that exceeds typical office broadband. |

## 2.2 Remote Access Model

Because the server is off-site, all interaction is digital. Two distinct access tiers ensure security for administrators and ease of use for staff:

Administrative Access (SSH)

Secure Shell uses encrypted key-pair authentication rather than passwords. Key-based SSH is virtually immune to brute-force attacks. Password login will be disabled entirely, and access will be restricted to known IP addresses via firewall rules.

Team / End-User Access (Web GUI)

Staff access all Hub services through standard web browsers at branded URLs (e.g. docs.company.com, projects.company.com). An Nginx reverse proxy sits in front of the application stack, listens on port 443 (HTTPS), terminates SSL/TLS encryption, and routes requests to the correct internal service based on the subdomain. The experience is identical to visiting any modern website.

Optional VPN Layer

A WireGuard VPN can be added so that Hub services are only reachable from within the corporate network tunnel, making them invisible to the public internet and reducing the attack surface to near zero.

## 2.3 Latency & Performance

Off-site hosting introduces a small network round-trip (typically under 10ms within the same country). However, the data centre’s bandwidth and uplink quality vastly exceed office broadband. Once the initial handshake completes, data transfers will be faster than accessing the same services over office Wi-Fi. SSD-backed storage ensures database-driven pages render in under 200 milliseconds.

# 3. Software Stack

## 3.1 Knowledge Base & Information Platform (Unified)

A single BookStack instance fulfils both the documentation wiki and the company information/release platform. BookStack organises content into Books, Chapters, and Pages — a familiar metaphor that non-technical staff can adopt immediately. Two leading open-source options were evaluated:

| Criterion | BookStack (Recommended) | Wiki.js (Alternative) |
| --- | --- | --- |
| Stack | PHP 8 / Laravel, MySQL/MariaDB | Node.js, PostgreSQL / MySQL / SQLite |
| Content Model | Books → Chapters → Pages. Maps naturally to policy documentation. | Flat wiki pages with folder tree. Flexible but needs more planning. |
| Editor | WYSIWYG + Markdown + built-in Draw.io diagrams. | Markdown-focused with visual editor. Strong code highlighting. |
| Ease of Use | Very low barrier. Non-technical staff contribute immediately. | Moderate. Some technical familiarity helpful. |
| Branding | Full: logo, colours, CSS, dark/light themes. Out of the box. | Theme support exists but custom theming requires code changes. |
| Authentication | LDAP, SAML 2.0, OpenID Connect, MFA. | Extensive: LDAP, OAuth, SAML, social providers. |
| Dev Status | Actively maintained. Regular releases and security patches. | Version 3.0 delayed since 2021. Community concerns on timeline. |

How the Information & Release Platform Works Within BookStack:

- A dedicated Book titled “Release Notes & Announcements” holds all company updates. Each release or policy change is a new Page with version numbers, dates, and changelogs.

- Staff subscribe to email notifications so they are alerted whenever new content is published.

- A lightweight landing page at hub.company.com can pull the three most recent announcements via BookStack’s API, acting as a central portal.

## 3.2 Custom Project Manager

Two open-source platforms were evaluated as Jira replacements. Both support self-hosting via Docker and run comfortably on the proposed 4-core VPS.

| Criterion | OpenProject | Taiga |
| --- | --- | --- |
| Methodology | Agile, Classic (Waterfall), and Hybrid. Gantt charts included. | Agile-only: Scrum and Kanban. No native Gantt or classic PM. |
| Key Features | Time tracking, budgeting, resource management, meetings, wiki module. | User stories, sprints, burn-down charts, issue tracking. Fast UI. |
| Interface | Comprehensive, enterprise-grade feel. More complex. | Minimal, modern, and fast. Praised for simplicity. |
| Community | 14,400+ GitHub stars. Very active. Frequent updates. | ~800 GitHub stars. Smaller community. Slower updates. |
| Security | LDAP, SSO, 2FA, GDPR-compliant, AES-256 (Enterprise). | LDAP by default. Fewer out-of-the-box security features. |

# 4. Migration Plan

Migrating from SharePoint to the self-hosted Hub requires a structured, phased approach to preserve content, maintain access, and minimise disruption.

| Phase | Activities | Deliverable |
| --- | --- | --- |
| Wk 1–2 | Catalogue all SharePoint content (wiki pages, docs, lists). Classify by priority. Map permissions to BookStack roles. | Content inventory spreadsheet and migration priority list. |
| Wk 2–3 | Provision VPS (Ubuntu Server LTS). Install Docker, Nginx, SSL (Let’s Encrypt). Deploy BookStack and PM tool. Configure DNS for branded subdomains. Harden server (disable password SSH, UFW firewall, optional VPN). | Running Hub environment accessible via branded URLs. |
| Wk 3–5 | Export SharePoint pages as HTML. Convert to Markdown via Pandoc. Import into BookStack (API or WYSIWYG paste). Rebuild hierarchy. Verify content and fix broken links. | Fully populated knowledge base with verified content. |
| Wk 5–6 | Pilot users across departments. Collect feedback on navigation, search, and accuracy. Iterate on branding and layout. Final content reconciliation. | UAT sign-off and refined branding. |
| Wk 6–7 | Company wide launch with guided introduction (video or live demo). Set SharePoint to read-only with redirect banner. Monitor performance for two weeks. Decommission SharePoint after 30-day parallel run. | Live Hub, onboarding materials, decommission plan. |

# 5. Post-Launch Testing Environment

Once the Hub is live, a dedicated staging/testing environment is essential. Applying updates, configuration changes, or plugin installations directly to the production system risks downtime and data corruption. A parallel test instance ensures that every change is validated before it reaches staff.

## 5.1 Why a Testing Environment Is Required

- Software updates to BookStack, OpenProject/Taiga, Nginx, or the operating system may introduce breaking changes or incompatibilities. A test instance catches these before they affect users.

- Configuration experiments (new permissions, branding tweaks, workflow changes) can be trialled safely without impacting live data.

- Security patches should be verified in staging before production deployment to confirm they do not break application functionality.

- Content structure changes (e.g. reorganising Books or project boards) can be previewed and approved by stakeholders before going live.

## 5.2 Architecture

The testing environment mirrors production but runs in isolation:

| Element | Detail |
| --- | --- |
| Hosting | Separate Docker containers on the same VPS, or a low-cost secondary VPS if resource isolation is preferred. |
| URLs | Accessed via test-docs.company.com and test-projects.company.com (separate Nginx server blocks). |
| Data | Periodically cloned from production using automated database snapshots. Test data is never pushed back to production. |
| Access | Restricted to administrators and designated testers only. Blocked from general staff via firewall or VPN rules. |
| Update Workflow | All updates applied to staging first → tested for 48–72 hours → approved → applied to production during a maintenance window. |

## 5.3 Cost Impact

If hosted on the same VPS, the testing environment adds negligible cost  only the additional disk space for database snapshots. Docker’s containerisation means the test instances share the same OS kernel and consume minimal extra RAM when idle. If a separate VPS is preferred for full isolation, a minimal 1–2 core instance is sufficient since the test environment will not handle concurrent user load.

# 6. Security Architecture

Security is designed in layers so that no single point of failure compromises the Hub:

| Layer | Mechanism | Purpose |
| --- | --- | --- |
| Transport | TLS 1.3 via Nginx with auto-renewing Let’s Encrypt certificates. | Encrypts all data in transit between the browser and the server. |
| Authentication | SSH key-pair for admins; LDAP / SSO / MFA for end users. | Eliminates password-based attacks; integrates with directory services. |
| Network | UFW firewall restricting open ports; optional WireGuard VPN. | Minimises exposure; VPN makes services invisible to the internet. |
| Application | Role-based access control (RBAC) within each tool. | Users see only the content and actions appropriate to their role. |
| Infrastructure | Docker container isolation; automated daily backups. | Limits blast radius of any compromise; enables rapid recovery. |

# 7. Next Steps

To move forward, the following approvals and actions are requested:

- Approve the proposed software stack: BookStack (unified wiki + announcements) plus OpenProject or Taiga (project management).

- Authorise budget for VPS hosting contract and domain name (if not already owned).

- Nominate a project lead and a pilot-user group of 5–10 staff.

- Confirm the requirement for a post-launch testing environment (same VPS or separate).

- Schedule a kick-off meeting to finalise the implementation timeline.

— End of Document —